## Instructions
Time Mission Site Review — How to use this sheet
Where to review | Staging URL lives in the email. Open it on your phone first, then desktop.
How to log feedback | Go to the Feedback tab. Add ONE ROW per issue — small, specific, one thing at a time.
Questions vs. feedback | Use the Feedback tab for things that need to CHANGE. Use the Questions tab for things Jefferson needs to DECIDE.
Dropdowns | Role, Device, Priority, and Status are dropdowns — just click the cell and pick.
Priority | Blocker = must fix before launch. Important = should fix. Nice-to-have = polish later.
Screenshots | Paste a link (Drive, Dropbox, etc.) in the Screenshot column. Helps a lot.
Deadline | End of Friday this week. Jefferson triages Monday, Ari starts full development Wednesday.
Things to focus on
• | Your location's details (address, phone, email, hours, photos)
• | Copy and tone — does it sound like Time Mission?
• | What's missing from the old site that you rely on
• | First impression on mobile AND desktop
Please ignore (prototype scope)
• | Book Now / Tickets buttons — being wired by Ari
• | Forms, tracking, cookie banner — pending
• | "Coming Soon" locations — intentional
• | Pixel-level polish — broken/off-brand is fair, but not 1-pixel alignment

## Feedback
# | Date | Reviewer | Role | Page URL | Device | Section | What you saw | What it should be | Priority | Screenshot link | Status | Jefferson's notes
1 | 2026-04-22 | Jefferson | Site Owner | — | — | — | EXAMPLE ROW — delete before launch. Use this row as a format reference. | Delete me. | Nice-to-have |  | Example
2 |  |  | TM Operator | /philadelphia.html | Mobile | Footer widget | Sunday hours show 10am–10pm but we are actually 12pm–10pm on Sundays | 12pm–10pm | Blocker |  | New
3 |  |  | LOL Owner | / | Desktop | Homepage hero | A first-time visitor doesn't immediately understand what Time Mission IS. | Add a short explainer ("Teams of 2–5 compete through 25+ challenge rooms") | Important |  | New
4 |  |  | Customer | /groups.html | Mobile | Gallery | Horizontal swipe on the gallery conflicts with page scroll on iOS Safari. | Lock horizontal scroll or add a clearer swipe indicator. | Nice-to-have |  | New

## Questions
# | Date | Reviewer | Role | Question | Context / page | Asked of | Answer | Status
1 | 2026-04-22 | Jefferson | Site Owner | EXAMPLE — delete before launch. Use this format for questions that need a DECISION (not a fix). | — | — | — | Example
2 |  |  | TM Operator | Should pricing be visible on location pages? | All location pages | Jefferson |  | Open
3 |  |  | LOL Owner | Are we bringing back "The Clock is Ticking" tagline? | Homepage title + hero | Jefferson |  | Open