## Master Timeline
TIME MISSION WEBSITE LAUNCH PLAN
Hard Deadline: May 22, 2026 (Before Houston Launch) ¦ Created: March 27, 2026
Phase | Task | Est. Time | Start Date | End Date | Owner | Status | Dependencies | Notes
1 | PHASE 1: FRAMEWORK MIGRATION |  | Mar 31 | Apr 11 |  |  |  | Foundation — blocks everything else
1 | Choose framework | — | Mar 27 | Mar 27 | Jefferson + Ari | Not Started | None | Eleventy or Astro recommended
1 | Set up project with build pipeline | 1 day | Mar 31 | Mar 31 | Jefferson | Not Started | Framework choice
1 | Extract shared CSS into single stylesheet | 1 day | Apr 1 | Apr 1 | Jefferson | Not Started | Project setup | ~500+ lines duplicated per page
1 | Create shared layout (head, nav, footer) | 1 day | Apr 2 | Apr 2 | Jefferson | Not Started | CSS extracted
1 | Migrate experiences, groups, gift-cards, FAQ, contact | 2 days | Apr 4 | Apr 7 | Jefferson | Not Started | Homepage done | 5 pages
1 | Migrate all 7 location pages + index | 2 days | Apr 8 | Apr 9 | Jefferson | Not Started | Main pages done | 8 pages total
1 | Fix all broken nav links (href='#') | 0.5 day | Apr 10 | Apr 10 | Jefferson | Not Started | Migration done | Location nav + social links
1 | Fix booking URLs per location | 0.5 day | Apr 10 | Apr 10 | Jefferson | Not Started | Migration done | All currently point to Philly
1 | Verify all pages render correctly | 1 day | Apr 11 | Apr 11 | Jefferson | Not Started | All migrated | MILESTONE: Framework complete
1 | Upload & Share GitHub | 1 day | Apr 3 | Aprl 3 | Jefferson | Not Started | Layout created | 3,179 lines → ~300 lines
2 | PHASE 2: CONTENT FIXES & MISSING PAGES |  | Apr 7 | Apr 18 |  |  |  | Parallel with Phase 1 end
2 | Collect real phone numbers for all locations | — | Apr 7 | Apr 7 | Jefferson (from TM) | Not Started | None | All currently 555 numbers
2 | Collect real social media URLs | — | Apr 7 | Apr 7 | Jefferson (from TM) | Not Started | None | Instagram, TikTok, Facebook
2 | Verify @timemission.com emails are active | — | Apr 7 | Apr 7 | Jefferson (from TM) | Not Started | None | 7 location emails
2 | Replace placeholder phone numbers + social links | 0.5 day | Apr 8 | Apr 8 | Jefferson | Not Started | Real data received
2 | Add Houston email + Antwerp phone number | 10 min | Apr 8 | Apr 8 | Jefferson | Not Started | Real data received | Missing from pages
2 | Flesh out Chicago location page | 1 day | Apr 9 | Apr 9 | Jefferson | Not Started | Phase 1 done | Currently 370 lines (sparse)
2 | Flesh out Houston location page | 1 day | Apr 10 | Apr 10 | Jefferson | Not Started | Phase 1 done | Priority — Houston launch
2 | Flesh out remaining 4 location pages | 2 days | Apr 11 | Apr 14 | Jefferson | Not Started | Phase 1 done | Lincoln, Manassas, W.Nyack, Antwerp
2 | Add real venue photos to location galleries | 1 day | Apr 15 | Apr 15 | Jefferson | Not Started | Photos from TM | Currently SVG placeholders
2 | Create Privacy Policy page | 0.5 day | Apr 16 | Apr 16 | Jefferson | Not Started | None | Legal review needed
2 | Create Terms of Service page | 0.5 day | Apr 16 | Apr 16 | Jefferson | Not Started | None | Legal review needed
2 | Create Cookie Policy + Accessibility Statement | 1 day | Apr 17 | Apr 17 | Jefferson | Not Started | None | GDPR required (Antwerp)
2 | Create 404 Error page | 0.5 day | Apr 18 | Apr 18 | Jefferson | Not Started | None | MILESTONE: All content complete
3 | PHASE 3: CMS INTEGRATION |  | Apr 7 | Apr 25 |  |  |  | Ari leads — 3 weeks
3 | Set up CMS account (Sanity.io recommended) | 1 day | Apr 7 | Apr 7 | Ari | Not Started | Framework chosen | Free tier: 3 users, 500K requests
3 | Design content models: Locations | 1 day | Apr 8 | Apr 8 | Ari + Jefferson | Not Started | CMS account | Name, address, phone, hours, booking URL
3 | Design content models: Experiences, FAQs, Pricing | 1 day | Apr 9 | Apr 9 | Ari | Not Started | CMS account
3 | Design content models: Pages, Announcements | 1 day | Apr 10 | Apr 10 | Ari | Not Started | CMS account
3 | Integrate CMS with static site generator | 3 days | Apr 11 | Apr 15 | Ari | Not Started | Models designed + Phase 1 | Critical integration work
3 | Migrate existing content into CMS | 2 days | Apr 16 | Apr 17 | Jefferson | Not Started | CMS integrated | Data entry
3 | Set up image CDN / optimization | 1 day | Apr 18 | Apr 18 | Ari | Not Started | CMS integrated | Auto-resize, WebP conversion
3 | Test: Jefferson edits + publishes without code | 1 day | Apr 21 | Apr 21 | Jefferson + Ari | Not Started | Content migrated | Must pass this test
3 | Set up user accounts + train Jefferson | 0.5 day | Apr 22 | Apr 22 | Ari | Not Started | CMS working
3 | CMS scheduling + buffer for fixes | — | Apr 23 | Apr 25 | Ari | Not Started | CMS working | MILESTONE: CMS operational
4 | PHASE 4: SEO |  | Apr 14 | Apr 25 |  |  |  | Jefferson + Claude Code
4 | Add meta descriptions to all pages | 1 day | Apr 14 | Apr 14 | Jefferson | Not Started | Phase 1 done | 150-160 chars, unique per page
4 | Add Open Graph + Twitter Card tags | 1 day | Apr 15 | Apr 15 | Jefferson | Not Started | Phase 1 done | For social sharing previews
4 | Add canonical URLs to all pages | 0.5 day | Apr 16 | Apr 16 | Jefferson | Not Started | Phase 1 done
4 | Generate sitemap.xml + robots.txt | 0.5 day | Apr 16 | Apr 16 | Jefferson | Not Started | Phase 1 done | Automate in build
4 | Add LocalBusiness structured data (all locations) | 1 day | Apr 17 | Apr 17 | Jefferson | Not Started | Phase 1 done | JSON-LD for Google rich results
4 | Add Organization + FAQ structured data | 1 day | Apr 18 | Apr 18 | Jefferson | Not Started | Phase 1 done
4 | Add alt text to all images | 1 day | Apr 21 | Apr 21 | Jefferson | Not Started | Phase 1 done | Accessibility + SEO
4 | Internal linking audit + improvements | 0.5 day | Apr 22 | Apr 22 | Jefferson | Not Started | All pages done
4 | Map old site URLs → new for 301 redirects | 1 day | Apr 23 | Apr 23 | Jefferson + Ari | Not Started | Old site crawled | Critical for SEO preservation
4 | Configure 301 redirects in hosting | 0.5 day | Apr 24 | Apr 24 | Ari | Not Started | URL map complete
4 | Verify with Google Rich Results Test | 0.5 day | Apr 25 | Apr 25 | Jefferson | Not Started | All SEO done | MILESTONE: SEO complete
5 | PHASE 5: ANALYTICS, GTM & PIXELS |  | Apr 21 | May 2 |  |  |  | Ari + Ryan coordination critical
5 | Create GTM container + install on all pages | 1 day | Apr 21 | Apr 21 | Ari | Not Started | Phase 1 done | Via shared layout = 1 install
5 | Grant GTM access to Ryan and Jefferson | 15 min | Apr 21 | Apr 21 | Ari | Not Started | GTM created
5 | Create/connect GA4 property | 0.5 day | Apr 22 | Apr 22 | Ryan | Not Started | GTM live
5 | Configure GA4 via GTM | 0.5 day | Apr 22 | Apr 22 | Ryan | Not Started | GA4 created
5 | Set up conversion events in GA4 | 1 day | Apr 23 | Apr 23 | Ryan + Ari | Not Started | GA4 configured | Book Now, forms, outbound clicks, calls
5 | Install Meta/Facebook Pixel via GTM | 0.5 day | Apr 24 | Apr 24 | Ryan + Ari | Not Started | GTM live | Ryan provides Pixel ID
5 | Install Google Ads conversion tag via GTM | 0.5 day | Apr 24 | Apr 24 | Ryan | Not Started | GTM live
5 | Install TikTok Pixel via GTM (if needed) | 0.5 day | Apr 25 | Apr 25 | Ryan | Not Started | GTM live | Confirm if running TikTok ads
5 | Set up Microsoft Clarity (free heatmaps) | 0.5 day | Apr 25 | Apr 25 | Ari | Not Started | GTM live | Free — no reason not to
5 | Add UTM parameters to Roller.app URLs | 0.5 day | Apr 28 | Apr 28 | Jefferson | Not Started | Phase 1 done | Track which page drives bookings
5 | Set up Google Search Console | 0.5 day | Apr 28 | Apr 28 | Ryan | Not Started | Domain verified
5 | Test all tracking with Tag Assistant | 1 day | Apr 29 | Apr 29 | Ari + Ryan | Not Started | All pixels installed
5 | Set up remarketing audiences + buffer | — | Apr 30 | May 2 | Ryan | Not Started | GA4 + Pixels live | MILESTONE: Tracking verified
6 | PHASE 6: FORMS & EMAIL |  | Apr 21 | May 2 |  |  |  | Parallel with Phase 5
6 | Set up form backend | 0.5 day | Apr 21 | Apr 21 | Ari | Not Started | Phase 1 done | Netlify Forms or Formspree
6 | Connect contact form + email notifications | 1 day | Apr 22 | Apr 22 | Ari | Not Started | Backend set up | Currently shows alert() only
6 | Set up group booking inquiry routing | 0.5 day | Apr 23 | Apr 23 | Ari + Jefferson | Not Started | Forms working | May need separate email
6 | Set up email marketing platform | 0.5 day | Apr 24 | Apr 24 | Ari | Not Started | None | Mailchimp/Klaviyo
6 | Connect newsletter signup form | 0.5 day | Apr 24 | Apr 24 | Ari | Not Started | Email platform set up
6 | Create welcome email for newsletter | 0.5 day | Apr 25 | Apr 25 | Jefferson | Not Started | Email platform set up
6 | Test all forms end-to-end | 0.5 day | Apr 28 | Apr 28 | Jefferson | Not Started | All forms connected | MILESTONE: Forms functional
7 | PHASE 7: LEGAL & COMPLIANCE |  | Apr 28 | May 9 |  |  |  | Required before launch
7 | Legal review of Privacy Policy + Terms | — | Apr 28 | Apr 28 | TM Owners (legal) | Not Started | Pages drafted (Phase 2)
7 | Install cookie consent tool | 1 day | Apr 29 | Apr 29 | Ari | Not Started | None | CookieBot or Osano
7 | Configure cookie categories | 0.5 day | Apr 30 | Apr 30 | Ari | Not Started | Consent tool installed | Necessary, analytics, marketing
7 | Ensure GTM respects cookie consent | 1 day | May 1 | May 1 | Ari | Not Started | GTM + consent tool | No pixels fire without consent
7 | GDPR-specific setup for Antwerp | 0.5 day | May 2 | May 2 | Ari | Not Started | Consent configured | EU visitors
7 | Accessibility audit (Lighthouse + WAVE) | 1 day | May 5 | May 5 | Jefferson | Not Started | All pages complete
7 | Fix critical accessibility issues | 2 days | May 6 | May 7 | Jefferson | Not Started | Audit done | Color contrast, keyboard nav, ARIA
7 | Final legal review | — | May 8 | May 9 | TM Owners | Not Started | All legal pages final | MILESTONE: Legally compliant
8 | PHASE 8: PERFORMANCE & QA |  | May 5 | May 16 |  |  |  | 2 weeks of testing
8 | Compress images (WebP, lazy loading) | 1 day | May 5 | May 5 | Jefferson | Not Started | All images added
8 | Minify CSS and JavaScript in build | 0.5 day | May 6 | May 6 | Ari | Not Started | Build pipeline
8 | Lighthouse audit — target 90+ all categories | 0.5 day | May 6 | May 6 | Jefferson | Not Started | Site complete
8 | Fix performance issues from Lighthouse | 1 day | May 7 | May 7 | Jefferson | Not Started | Audit done
8 | Cross-browser testing (Chrome, Safari, Firefox, Edge) | 1 day | May 8 | May 8 | Jefferson + Ari | Not Started | Site complete
8 | Mobile testing (iOS Safari, Android Chrome) | 1 day | May 9 | May 9 | Jefferson + Ari | Not Started | Site complete
8 | Test all booking flows end-to-end | 1 day | May 12 | May 12 | Jefferson | Not Started | All URLs correct | Every location
8 | Test forms + verify tracking | 1 day | May 13 | May 13 | Jefferson + Ari + Ryan | Not Started | All integrated
8 | Link audit + social sharing previews | 1 day | May 14 | May 14 | Jefferson | Not Started | All pages done | Facebook debugger, Twitter validator
8 | Fix all QA issues | 2 days | May 15 | May 16 | Jefferson + Ari | Not Started | QA complete | MILESTONE: QA passed
9 | PHASE 9: STAGING & STAKEHOLDER REVIEW |  | May 12 | May 18 |  |  |  | 1 week review
9 | Deploy to staging URL | 0.5 day | May 12 | May 12 | Ari | Not Started | QA in progress | preview.timemission.com or similar
9 | Jefferson full review of staging | 1 day | May 13 | May 13 | Jefferson | Not Started | Staging deployed
9 | TM Owners review staging site | 2 days | May 14 | May 15 | TM Owners | Not Started | Staging deployed | Collect all feedback
9 | Collect and prioritize feedback | 0.5 day | May 16 | May 16 | Jefferson | Not Started | Reviews complete
9 | Implement critical fixes from feedback | 2 days | May 17 | May 18 | Jefferson + Ari | Not Started | Feedback collected | MILESTONE: Stakeholder approved
10 | PHASE 10: GO LIVE |  | May 19 | May 22 |  |  |  | Launch week
10 | Final pre-launch checklist review | 0.5 day | May 19 | May 19 | Jefferson + Ari | Not Started | Staging approved
10 | TM Owners update DNS to new hosting | 0.5 day | May 19 | May 19 | TM Owners | Not Started | Hosting ready | Do on Monday, not Friday
10 | Verify SSL + site loads on production | 0.5 day | May 19 | May 19 | Ari + Jefferson | Not Started | DNS switched
10 | Configure 301 redirects from old URLs | 0.5 day | May 20 | May 20 | Ari | Not Started | Site live
10 | Submit sitemap to Google Search Console | 15 min | May 20 | May 20 | Ryan | Not Started | Site live
10 | Verify all tracking on production | 0.5 day | May 20 | May 20 | Ari + Ryan | Not Started | Site live | Use Tag Assistant
10 | Test all forms + booking links on production | 0.5 day | May 20 | May 20 | Jefferson | Not Started | Site live
10 | Monitor Day 1 | — | May 21 | May 21 | All | Not Started | Site live
10 | Monitor Day 2 | — | May 22 | May 22 | All | Not Started | Site live | MILESTONE: SITE IS LIVE

## Pages & Elements
PAGES
REQUEST BY: April 3, 2026 ¦ HARD DEADLINE: April 14, 2026
Page | Details | Location(s) | Deadline | Status
Home |  |  |  | Not Started
About |  |  |  | Not Started
Parties & Groups |  |  |  | Not Started
FAQs |  |  |  | Not Started
Locations |  |  |  | Not Started
Not Started
Not Started
Not Started
Gift Cards |  |  |  | Not Started
Help & Support |  |  |  | Not Started | https://www.puttshack.com/support/
Press Room |  |  |  | Not Started
Not Started
Not Started
Terms & Conditions |  |  |  | Not Started
Privacy Policy |  |  |  | Not Started
Not Started
Not Started
Not Started
Not Started
Not Started

## Content Needed from TM
CONTENT NEEDED FROM TM OWNERS
REQUEST BY: April 3, 2026 ¦ HARD DEADLINE: April 14, 2026
Item | Details | Location(s) | Deadline | Status
Real phone numbers | Replace all 555 test numbers | All 7 locations | Apr 14 | Not Started
Antwerp phone number | Currently missing entirely | Antwerp | Apr 14 | Not Started
Social media URLs | Instagram, TikTok, Facebook account links | Brand-level | Apr 14 | Not Started
Verify email addresses work | philadelphia@, chicago@, houston@, etc. | All 7 locations | Apr 14 | Not Started
Venue photos per location | Lobby, rooms, exterior, storefront | All 7 locations | Apr 14 | Not Started
Operating hours (confirm accuracy) | Days + hours for each location | All 7 locations | Apr 14 | Not Started
Houston-specific launch details | Special hours, opening date, promo info | Houston | Apr 14 | Not Started
Roller.app booking URLs (confirm) | Verify each location's URL is correct | All 7 locations | Apr 7 | Not Started
Privacy Policy | Existing doc or approve draft for legal review | N/A | Apr 28 | Not Started
Terms of Service | Existing doc or approve draft for legal review | N/A | Apr 28 | Not Started
DNS access / hosting account | Credentials or point of contact for DNS switch | N/A | May 12 | Not Started
Google account ownership | Who owns the Google Business / Analytics accounts? | N/A | Apr 14 | Not Started

## Risks
RISKS & MITIGATIONS
Risk | Impact | Likelihood | Mitigation
Ari's agency slow or overcommitted | CMS + analytics delayed → launch slips | Medium | Get timeline commitment in writing today. Fallback: Decap CMS (free, self-setup).
TM Owners slow to provide content | Placeholder content at launch | High | Send request by Apr 3 with hard deadline Apr 14. Follow up weekly.
Framework migration takes longer | Everything shifts right | Low | Start Mar 31. If stuck by Apr 7, fall back to CSS extraction only.
Ryan unavailable for pixel setup | No tracking at launch = blind ad spend | Medium | Schedule Ari+Ryan call NOW for April 17. Pixels can't wait.
DNS switch goes wrong | Site down on launch day | Low | Do DNS change Monday (May 19), never Friday. Have rollback plan.
Legal review takes too long | Launch without privacy policy = legal risk | Medium | Use Termly/iubenda template generator as stopgap. Replace with reviewed version later.
Roller.app booking URLs change | Booking broken = lost revenue | Low | Confirm all URLs with TM operations by Apr 7. Store in CMS for easy updates.
Scope creep from stakeholder review | QA and launch delayed | High | Only fix critical issues from review. Nice-to-haves go to V2 backlog.

## Weekly Check-Ins
WEEKLY CHECK-IN TRACKER
Week | Date | Focus Phase(s) | Key Deliverables | Blockers | Notes
1 | Mar 31 | Phase 1: Framework | Project setup, CSS extraction, shared layout
2 | Apr 7 | Phase 1 + 2 + 3 start | Migration complete, content collection, CMS setup begins | Waiting on TM content
3 | Apr 14 | Phase 2 + 3 + 4 | Location pages done, CMS models, SEO started | TM content deadline Apr 14
4 | Apr 21 | Phase 3 + 4 + 5 + 6 | CMS test, SEO done, GTM live, forms working | Ari+Ryan call must happen | Add Ryan to check-ins
5 | Apr 28 | Phase 5 + 6 + 7 | Pixels installed, forms tested, legal review
6 | May 5 | Phase 7 + 8 | Compliance done, QA begins, images optimized
7 | May 12 | Phase 8 + 9 | QA complete, staging deployed, stakeholder review |  | Critical week
8 | May 19 | Phase 10: LAUNCH | DNS switch, go live, verify everything |  | LAUNCH WEEK

## Critical Path
CRITICAL PATH — IF THESE SLIP, LAUNCH SLIPS
# | Critical Item | Deadline | Why It Blocks Everything
1 | Framework migration complete | Apr 11 | CMS, SEO, analytics, and forms all require the shared layout to be in place. Without it, every change touches 15 files.
2 | CMS integrated and working | Apr 25 | Jefferson can't manage content without it. Weekly updates require CMS before launch.
3 | Real content from TM Owners | Apr 14 | Phone numbers, photos, social links, legal docs. Can't launch with 555 numbers and placeholder images.
4 | Ari + Ryan coordination call | Apr 17 | GTM structure and pixel IDs must be agreed before analytics work begins in Week 4.
5 | All tracking verified | May 2 | Without verified tracking, ad spend after launch generates no measurable ROI.
6 | Stakeholder review complete | May 18 | TM Owners must approve before DNS switch. Build in time for feedback rounds.
7 | DNS switch scheduled with TM Owners | May 19 | They control the domain. Must be scheduled in advance — not day-of.